## Data
Impact_ID | ECR_ID | Affected_Entity_ID | Impact_Dimension | Propagation_Level | Status | Rationale | Recommended_Action
IMPACT-0001 | ECR-001 | BAT-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0002 | ECR-001 | BMS-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0003 | ECR-001 | ENC-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0004 | ECR-001 | THM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0005 | ECR-001 | FAN-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0006 | ECR-001 | CAB-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0007 | ECR-001 | CON-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0008 | ECR-001 | CHR-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0009 | ECR-001 | FRM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0010 | ECR-001 | SW-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0011 | ECR-001 | SNS-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0012 | ECR-001 | REQ-001 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0013 | ECR-001 | REQ-003 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0014 | ECR-001 | REQ-008 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0015 | ECR-001 | REQ-013 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0016 | ECR-001 | REQ-014 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0017 | ECR-001 | REQ-015 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0018 | ECR-001 | REQ-016 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0019 | ECR-001 | TEST-001 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0020 | ECR-001 | TEST-004 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0021 | ECR-001 | MFG-002 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0022 | ECR-001 | SRV-001 | Service | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0023 | ECR-004 | THM-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0024 | ECR-004 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0025 | ECR-004 | ENC-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0026 | ECR-004 | FRM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0027 | ECR-004 | FAN-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0028 | ECR-004 | REQ-013 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0029 | ECR-004 | REQ-008 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0030 | ECR-004 | TEST-004 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0031 | ECR-004 | MFG-006 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0032 | ECR-005 | CHR-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0033 | ECR-005 | CHG-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0034 | ECR-005 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0035 | ECR-005 | CAB-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0036 | ECR-005 | CON-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0037 | ECR-005 | REQ-017 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0038 | ECR-005 | REQ-005 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0039 | ECR-005 | TEST-005 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0040 | ECR-006 | MTR-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0041 | ECR-006 | INV-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0042 | ECR-006 | CAB-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0043 | ECR-006 | CON-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0044 | ECR-006 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0045 | ECR-006 | SW-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0046 | ECR-006 | REQ-006 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0047 | ECR-006 | REQ-005 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0048 | ECR-006 | TEST-006 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0049 | ECR-007 | INV-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0050 | ECR-007 | CAB-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0051 | ECR-007 | CON-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0052 | ECR-007 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0053 | ECR-007 | MTR-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0054 | ECR-007 | SW-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0055 | ECR-007 | REQ-005 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0056 | ECR-007 | TEST-007 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0057 | ECR-008 | CAB-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0058 | ECR-008 | CON-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0059 | ECR-008 | INV-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0060 | ECR-008 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0061 | ECR-008 | FRM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0062 | ECR-008 | REQ-005 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0063 | ECR-008 | REQ-008 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0064 | ECR-008 | TEST-008 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0065 | ECR-008 | MFG-008 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0066 | ECR-009 | CON-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0067 | ECR-009 | CAB-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0068 | ECR-009 | INV-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0069 | ECR-009 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0070 | ECR-009 | REQ-005 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0071 | ECR-009 | TEST-009 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0072 | ECR-009 | MFG-009 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0073 | ECR-015 | BAT-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0074 | ECR-015 | BMS-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0075 | ECR-015 | ENC-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0076 | ECR-015 | THM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0077 | ECR-015 | FAN-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0078 | ECR-015 | CHR-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0079 | ECR-015 | SW-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0080 | ECR-015 | SNS-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0081 | ECR-015 | REQ-004 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0082 | ECR-015 | REQ-013 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0083 | ECR-015 | REQ-015 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0084 | ECR-015 | TEST-015 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0085 | ECR-015 | SUP-001 | Supplier | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0086 | ECR-015 | SUP-002 | Supplier | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0087 | ECR-016 | ENC-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0088 | ECR-016 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0089 | ECR-016 | THM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0090 | ECR-016 | FRM-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0091 | ECR-016 | REQ-004 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0092 | ECR-016 | REQ-008 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0093 | ECR-016 | REQ-013 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0094 | ECR-016 | TEST-016 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0095 | ECR-016 | MFG-016 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0096 | ECR-016 | SRV-009 | Service | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0097 | ECR-013 | FRM-001 | Component | Direct | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0098 | ECR-013 | BAT-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0099 | ECR-013 | ENC-001 | Component | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0100 | ECR-013 | REQ-008 | Requirement | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0101 | ECR-013 | TEST-010 | Validation | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0102 | ECR-013 | MFG-010 | Manufacturing | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release
IMPACT-0103 | ECR-013 | SRV-010 | Service | First/second-order | Expected | Relationship and engineering dependency require review. | Validate before release

## README
Metadata | Value
Dataset | Aureon E-Move X1 PLM Agent Dataset
Version | 1.0
Purpose | Synthetic research-grade PLM world for agentic AI, RAG, tool use and engineering change impact analysis.
Product | Aureon E-Move X1 electric scooter
Company | Aureon Mobility Systems Pvt. Ltd. (fictional)
Ground Truth | Evaluator-only; do not expose to agent during benchmark evaluation.
Status | Freeze as V1 baseline; future modifications become V1.1/V2.